## Sheet1
Period | Tasks | Status
Week 1-2 (Mar 1-14) | Topic selection, domain finalised (Finance + Law), literature review, A100 environment setup | Done
Week 3 (Mar 15-21) | Dataset collection: FinanceBench, HotpotQA dev set; BM25 indexing of FinanceBench and HotpotQA; initial Recall@3 baseline | Done
Week 4 (Mar 22-28) | Dataset collection: CUAD, LegalBench-RAG-mini; BM25 indexing of all four corpora; Contriever integration + FAISS indexing | In Progress
Week 5 (Apr 1-7) | Hybrid RRF implementation; LangChain RetrievalQA chain scaffolding; Connect LLaMA-3.1-8B-Instruct and Qwen2.5-7B-Instruct generators; HotpotQA retrieval precision analysis (BM25 vs Contriever vs Hybrid) | Planned
Week 6 (Apr 8-14) | Full 3x2x2 RAG grid baseline runs; zero-shot vs instruction-tuned ablation on Qwen2.5-7B base vs Instruct | Planned
Week 7 (Apr 15-21) | Hallucination evaluation (FActScore, LangChain Structured Chain, Self-RAG); cross-domain performance comparison | Planned
Week 8 (Apr 22-26) | Report writing and analysis; Presentation slides, final code cleanup, end-to-end demo | Planned